## PDM
Predicting Stock Market Trends Using Machine Learning Model (LSTM)
Project Start Date: | 2024-05-14 |  |  | Lecture |  | Quiz |  | Submission |  | Supervisor Meeting |  | Coding Preparation |  | Viva |  | Report Preparation
PROJECT KEY:
|  |  | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17 | 2024-06-24 | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-09-01
TASK | DESCRIPTION | TASK DATES | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16
Lecture - 1 | Module overview and choosing a project | 2024-05-14 | 2024-05-13: Lecture - 1
Lecture - 2 | Project plan and literature search | 2024-05-21 | 2024-05-20: Lecture - 2
choosing a project | Agree topics and dataset with supervisors by email | 2024-05-22 | 2024-05-20: Topic: Stock Market
Supervisor Meeting - 1 | Discussed the Project Topics | 2024-05-21 | 2024-05-27: Initial Plan
Lecture - 3 | Data Ethics and PDM Preparation | 2024-06-03 | 2024-06-03: Lecture - 3
Supervisor Meeting - 2 | PDM Presentation | 2024-06-13 | 2024-06-03: PDM Preparation; 2024-06-10: PDM Presentation
Lecture - 4 | Data Ethics | 2024-06-17 | 2024-06-17: Lecture - 4
Supervisor Meeting - 2 | Literature and Coding Discussion | 2024-06-21 | 2024-06-17: Literature preparation
Quiz | Ethics Quiz | 2024-07-02 | 2024-07-01: Quiz
Literature Review | Research on LSTM-based stock market analysis | 1 Jul - 10 Jul | 2024-07-01: Literature Review
Lecture - 5 | Results and Preparation of FPR and viva | 2024-07-15 | 2024-07-15: Lecture - 5
Coding | Investigate featuring | 17 Jun - 30 Jun | 2024-06-17: Investigate featuring
| Data Preprocessing | 1 Jul - 14 Jul | 2024-07-01: Data Preprocessing; 2024-07-29: Mock Viva; 2024-08-05: Mock Viva
| Dataset Analysis with Model | 1 Jul - 28 Jul | 2024-07-01: Dataset Analysis with LSTM Model
| Data Visualization | 15 Jul - 28 Jul | 2024-07-15: Data Visualization
| Prediction Evaluation | 22 Jul - 31 Jul | 2024-07-22: Prediction
Final Report Preparation | Write a Summary | 29 Jul - 7 Aug | 2024-07-29: Summary
| Describe the Methodology and Background | 29 Jul - 7 Aug | 2024-07-29: Methodology and Background
| Compose the Outcomes | 8 Aug - 14 Aug | 2024-08-05: Results
| Add a Conclusion | 15 Aug - 18 Aug | 2024-08-12: Conclusion
| Report Submission | 19 Aug - 23 Aug | 2024-08-19: Submit FPR
Viva | Viva Preparation | 1 Sep - 10 Sep | 2024-09-01: Viva Preparation
| Viva Meeting | 11 Sep - 19 Sep | 2024-09-01: Viva